## Slide 1
Benefit Management Framework
Stephanie Chadwick
April 2022
1.0
Version | Date | Updated by: | Summary of changes

## Slide 2
Benefits Management Framework
Benefits Management is the approach to the identification, quantification, analysis, planning, tracking, realisation and optimisation of benefits.
This framework sets out common terminology and how the University will;
identify
record
track and monitor
and report the benefits from the SCO portfolio of change.

## Slide 3
What is a benefit
A benefit is the measurable improvement from change, which is perceived as positive by one or more stakeholders, and which contributes to the organisations strategic objectives.
Benefits should be recorded in project documentation so that they meet the following criteria:
Specific – always start a benefit description with a change term at the beginning, e.g. increase in, reduction of etc. avoid using ‘improvement in…’ as this is too vague.
Measurable – tangible qualitative or quantitative evidence and measures should be recorded to show the progress made towards realisation
Achievable – ensure that benefits can be realised within a certain timeframe and include this target date in the realisation plan
Relevant – align benefits with the organisations values and strategic objectives via a benefit map
Timebound – set realistic end dates for benefit realisation
Five steps for effective Benefits Realisation is a useful short video to watch on YouTube
Managing Project Benefits is a course on LinkedIn learning (access to LinkedIn Learning can be given here)

## Slide 4
Align benefits with strategy
Understand how the planned change contributes to the organisations strategic objectives,
Start with the end in mind if possible
  Look at what benefits need to be realised to support the strategic objectives
This will help score and prioritise projects.
  Use these to determine the project objectives, deliverables and business change.
Use successful delivery methods
Integrate benefits with key performance indicators
Use clear business case information, stage gateways and staged release of funding to ensure confidence in delivery.
Manage benefits from a portfolio perspective
Link benefit measures to existing KPIs or balanced scorecards
Ensure that projects are aligned with strategic objectives and good practice is repeatable across the change portfolio.
Align responsibilities for benefits realisation with the owners specified in Business Cases.
Approach

## Slide 5
Principles of Benefits Management
Benefits Management Principle |  | End State Capability
Accountability follows funding | Those funding the benefits will be accountable for their realisation | Benefit owners are empowered to deliver benefits
Benefits-led decision making | Decision making will be expected to optimise overall benefits from the Core and Wider Programmes | Governance and assurance mechanisms for benefits management identified and embedded Benefits management used as part of BAU project development and delivery to protect & optimise benefits Decisions consider impact on benefits as well as whole life cost
Continuous improvement | The Core & Wider Programmes will continuously strive to find additional benefits | Stakeholders are actively encouraged to suggest innovations which improve the delivery of benefits or mitigate dis-benefits Projects are reviewed to establish the effectiveness of benefit realisation A culture of continuous improvement and opportunity identification is embedded within the benefits management processes across the programme
Benefits-led performance | The realisation of benefits will be at the heart of the Core & Wider Programmes’ performance management | Strategic goals and objectives drive performance and behaviours across the whole programme Organisational scorecard drives performance of the organisation and its supply chain Other organisations are encouraged and supported to align their performance frameworks to the strategic goals and objectives
Regular monitoring | Best in class integrated benefits reporting will help accountable and responsible parties realise benefits | High quality data available for reporting to wider stakeholders and for use in evaluation of the programme Effective benefit reporting is embedded and operational (Please see Appendix A for further info on reporting benefits) Under-performance of benefit delivery is actively managed

## Slide 6
Key Roles and Responsibilities
(These are the roles with day to day involvement throughout the whole of the benefit lifecycle - for additional roles please see appendix B)
Role | Benefit management responsibilities
Sponsor | Champions the change, provides strategic leadership. Is accountable for a project / programme meeting its objectives and optimising benefit realisation. Owns the Business Case including the overall cost-benefit position and approves the benefit realisation plan. Chairs benefit reviews
Programme / Project Manager | Responsible for the day to day management of the project / programme Develops the benefit realisation plan in consultation with the BCM Develops the business case
Business Change Manager | The role responsible for facilitating benefit management from identification through to realisation. Provides input to the benefit realisation plan Identifies and quantifies benefits with the support of business managers Advises the sponsor on business readiness Engages with Benefit Owners and key stakeholders to ensure change is implemented smoothly Monitors and reports on benefit realisation post closure
Benefit Owner | The individual within the organisation that will be responsible for ensuring that the improvements are realised and embedded.
Benefit Analyst | Writes and maintains the benefit management framework and reviews business cases to ensure compliance. Trains other SCO staff on the use of the benefit management framework and provides support to Project and Programme Managers to ensure that there is an effective approach to benefits management applied across the SCO. Maintains an up to date portfolio level benefit plan Participates in post implementation reviews and monitors issues arising
PMO Analyst | Updates benefit information and supports the Business Change Manager, Project Managers and Benefit Analyst where appropriate.

## Slide 7
Definitions
Term | Definition | Example
Objective | What the project is planning to achieve, this should link to the scope of the project. | To deliver a compliant data solution in line with the conditions of registration and our mandatory responsibilities.
Deliverable | The goods or services produced as a result of a project that are intended to be delivered to a customer, also known as a capability or an output. | Introduction of new IT system with compliant data fields to support automated returns
Business Change | How things are done differently when an organisation improves, restructures or transforms a part of its operations, also known as an outcome. | Mandatory compliance with data requirements
Measure | How the improvement will be evidenced in terms of KPIs | Cost avoidance of £Xm in potential fines.
Observable outcome | A positive outcome from the implemented change that can’t be measured or is difficult to measure but can be used as good news stories and in project communications, usually described as an intangible benefit. | The core data held by the University is more resilient and as a result analytics are improved.

## Slide 8
What good looks like
How benefits should be worded and described in project documentation |  | 
Benefits description (or Disbenefit) | This should describe the improvement (or disimprovement) you expect to see, this should be measurable and explained in change terms, e.g. ‘Increase in the income generated from A during an academic year from £Xm to £Ym over a 5 year period which will be used to……’ | 
Measure | This should say what measure you are using and the source of the information, e.g. increase in income generated against finance code XXXX between 1st Oct and 31st Sept. | 
Type | Financial – can be measured in £s (Project Accountant to assist) | Non-Financial – measured in hrs, %, scores
Category For definitions and examples please see appendix C1 and C2 | Cost reduction Increase in surplus generating income / revenue Cost avoidance | Risk avoidance / reduction Compliance Increase in staff satisfaction Increase in student satisfaction Increased efficiency Increased productivity Positive impact on reputation and / or brand awareness
Owner | The person in the organisation who will be responsible for the realisation of the benefit and ensures that it is tracked and monitored and any variance from the target explained. | 
Baseline Date | This is the date that is used to measure the expected improvement against. It is usually just before go live, however it can be on day 1 of the change if the change brings about the measurement method. | 
Baseline Value | This is the value that the improvement is measured against and is taken on the baseline date specified | 
Timescale for realisation | The overall timeframe that the benefit will be realised within | 
Frequency of monitoring | This is how often measures will be collected e.g. monthly, quarterly, yearly etc. | 

## Slide 9
Benefit activity in project lifecycle
Phase | Scope |  | Define |  | Design and plan |  | Readiness |  | Implement Review and Close |  | Business as Usual
Overall Goal | Agree strategic need | Gateway 1: Strategic Opportunity Case | Confirm viability within financial envelope | Gateway 2: Outline Business Case Approval | Confirm initiative is set up for success and continued viability within financial envelope | Gateway3: Full Business Case Approval | Confirm continued viability and product meets quality criteria within financial envelope | Gateway 4: Pre-Implementation Approval | Confirm that we have delivered what we said we would and that the University is able to sustain the changes | Gateway5: Post Initiative and Benefits Review | Change and new ways of working are embedded and sustained.
Benefit specific objectives | Understanding of the high level anticipated benefits |  | Validation and identification of the expected detailed benefits |  | Finalisation of the benefit realisation plan with timescales and targets. |  | Confirmation that benefit realisation is on track |  | Change is implemented and benefits are beginning to be realised. |  | Change is embedded and benefits are tracked and reported on.
Benefit specific activity | Identify the high level benefits and link to the strategic objectives in the University 5 year plan |  | Validate and analyse the benefits and link them to the deliverables and objectives of the project and the university strategic goals. Identify and confirm owners. |  | Update and finalise the benefits map and plan and identify corresponding measures. |  | Baseline and plan for benefit realisation Identify additional emergent benefits and update the benefit realisation plan. Take baselines of measures. |  | Report benefits and assess initial benefits realisation Plan for Post Implementation Review |  | Track and monitor benefits and take appropriate action where required. Conduct a Post Implementation Review
Artefacts | Strategic Business Case |  | Outline Business Case Draft Benefit Map Draft Benefit Realisation Plan. Gateway Pack |  | Full Business Case Final Benefit Map Baselined Benefit Realisation Plan Gateway Pack |  | Updated Benefit Realisation Plan Updated Benefit Map (if required) Gateway Pack |  | Updated Benefits Realisation Plan Closure Report Gateway Pack |  | Updated Benefits Realisation Plan Post Implementation Review
CRs to include a benefit impact assessment
Deliverables built
Deliverables implemented
Business change embeds
Benefits tracked to realisation
Outputs Outcomes Benefits

## Slide 10
Scope
Define
Design & Plan
Implement, Review & Close
Readiness
Identify: Expected high level benefits
The Strategic Business Case should contain the following information:
If the project is a regulatory or legal requirement and if it is what the main benefit will be, for example;
  Risk reduction – e.g. our network is more secure and use a risk score.
  Risk avoidance – e.g. risk of system running out of support is eliminated and use a risk score.
  Cost avoidance – e.g. fines will be avoided and included the value of possible fine.
If the project is not regulatory or legal requirement list the top six high level benefits that the project expects to deliver. These should be quantified with a change term at the beginning – increased, reduced, faster etc.
Show how the project benefits link to the five year plan and the strategic objectives of the University and measures of success.
Include an estimated range of the high level costs of the project.

## Slide 11: Validate: Analysis of benefits
Scope
Define
Design & Plan
Implement, Review & Close
Readiness
In order to validate the benefit information a Benefit Mapping workshop should be carried out during the Define stage. This should be undertaken with stakeholders that are likely to be impacted by the project as well as those who have the capacity to make decisions e.g. sponsors and other senior executives. An example Benefit Map is shown in Appendix D and an example pack to help deliver a mapping session can be found at Appendix E.
By getting sign-up at the early stage of the process there will be a common understanding of the project aims and what the likely benefits for stakeholders will be.
The Benefit Log and Realisation Plan should be populated with the information from the mapping session and then the information can be copied into the Outline Business Case which should include
Updated and validated benefit descriptions and who will own them, this should also include any disbenefits that are identified.
The business changes and deliverables required to ensure the benefits are realised and,
How these link to the objectives of the project, any programme or business objectives already specified and the overall university 5 year plan.

## Slide 12
Scope
Design & Plan
Implement, Review & Close
Readiness
Define
Refine: Update of Benefits Realisation Plan
A further Benefit Mapping session should be held during Design and Plan in order provide clarity in the business around how benefits will be realised and to populate the Full Business Case with confirmed;
Benefits and the Business Changes required to deliver them.
Project Objectives and links to the University 5 year plan and Programme Objectives if appropriate.
Benefit owners, measures and data collection methods that will be used to show success and provide clarity on how the benefits will be realised.
This information should be updated in the Benefit Realisation Plan and then copied into the relevant section of the Full Business Case - example below.

## Slide 13
Scope
Design & Plan
Implement, Review & Close
Readiness
Define
Finalise: Agree the measures and data collection methods
In Design and Plan appropriate measures and data collection methods should be agreed and finalised with Benefit Owners and the Sponsor to show project success and provide clarity on how the benefits will be realised. This will help to:
Communicate what is regarded as important and contributes to an understanding of what constitutes success.
Provide a basis for tracking and managing benefit realisation
Provide a basis for accountability and ensure that benefits claimed are reasonable and plans are put in place for realisation.
Good measures should be:
Efficient: Make use of data available form the current performance management system where possible.
Effective: Avoid negative unintended consequences, drive the right behaviour and be reliable
Sufficient: Measures should provide sufficient assurance that the key underlying benefits have been realised.
These measures should then link through to the organisations strategic goals.

## Slide 14
Scope
Design & Plan
Implement, Review & Close
Readiness
Define
Baseline: Plan for benefit realisation
Ensure that deliverables are fit for purpose and can be integrated into the business area.
Plan for benefit realisation and engage with benefit owners in order to ensure benefits are achievable.
Take baselines in preparation for data collection and benefit realisation
Include any emergent benefits and measures in the benefit map and update the benefit realisation plan.
Build expected benefit realisation into financial forecasts, resource plans, performance targets, operational and strategic plans.

## Slide 15
Closure: Closure report and Gateway
Scope
Define
Design & Plan
Implement, Review & Close
Readiness
Use the Project Closure Report and the Gateway to show;
Which benefits will be achieved pre and post-closure and what the overall expected benefits will be, see table below which can be copied over from the benefit toolkit.
If there are any deviations from the approved Business Case with the reason, refer to Change Requests for the detail as to why this has happened.
If there any emergent benefits to be delivered that were not previously identified
Timescales and frequency of reporting
Include the plan for the Post Implementation Review in the Project Closure report, and specify when it should be held and who should be involved

## Slide 16
Track and Report: Benefit Dashboard
Scope
Define
Design & Plan
Implement, Review & Close
Readiness
Benefit realisation should be monitored and recorded in the Benefit Log by the Project Manager after go live and during the warranty period and then by the Benefit Owner after closure for the amount of time specified in both the log and the closure report.
Benefit owners should ensure processes are embedded into BAU and then track benefits in the log and report at agreed intervals to the PMO in order to consolidate at portfolio level.
A table similar to the one below can be used to report the progress of benefit realisation, any risks and any mitigation that needs to be put in place in order to get benefit realisation back on track to SLT and into PMO.
Benefit RAG | Benefit in each category – list which benefits are considered to be red / amber / green | Commentary - include comments regarding the reasons why benefits aren’t on track and if any mitigating actions are necessary or can be taken.
 |  | Benefit realisation on track.
 |  | Expected benefits are being realised but realisation date has moved out OR realisation date is the same but expected benefits are less than forecast
 |  | Benefit realisation is at significant risks and not on target to realise expected benefits in target timescales.

## Slide 17
Track and Report: Reporting against realisation plan
Scope
Define
Design & Plan
Implement, Review & Close
Readiness
If more information is required to understand why a benefit is not on track then additional information can be reported in a similar format to the below.
Initiative | Description | Target £m | Year
21/22
22/23
23/24
25/26
Progress towards £m
£8m
£22.4m
Savings by year - example
Pay benefits backed
by firm plans
Non - pay benefits
backed by firm plans
17

## Slide 18
Appendices
Reporting and governance.
Additional roles supporting the benefit management process
Definitions of benefit categories
Example of a Benefits Map
Template - Benefits Mapping Workshop Purpose & Structure

## Slide 19
Appendix A – Reporting and Governance
Point in lifecycle | What to report | Who reports
Strategic Business Case | The high level benefits | Sponsor / Demand Manager
Outline Business Case | Refined and validated benefits | Project / Programme Manager
Final Business Case | Confirmed and approved benefits | Project / Programme Manager
Closure Report | Benefits realised as part of closure and timescales for realisation for other benefits. | Project / Programme Manager
Post Closure | Regular benefit RAG reporting | Benefit Owner and Benefit Analyst

## Slide 20
Appendix B – Additional roles supporting the benefit management process
Role | Benefit management responsibilities
Data Analyst | Contributes data insights in support of benefit process
Business Analyst | Contributes business process performance baselines and forecasts
Senior Financial Analyst | Provides information on baseline budgets to PMs in order for them to assess the extent of financial savings that can be made by the project. Assist with how this is tracked and reported on in future after Go Live.

## Slide 21
Appendix C1 – Definitions of benefit categories
Category | Definition
Cost reduction | A decrease in the University’s future spend, it involves identifying and removing previously identified budgeted expenditures.
Increase in surplus generating income / revenue | Increase in the amount of surplus generated by the University in terms of charitable donations, fees etc. If these need to be spent in a specific way please include this in the business cases specify if budget relieving or not.
Cost avoidance | The avoidance of incurring unplanned or unbudgeted future costs e.g. this could relate to avoidance of fines, increases in contract costs etc.
Risk avoidance | The elimination of events that can negatively affect the University.
Risk reduction | Reduction in the frequency or severity of events that can negatively affect the University.
Increase in staff satisfaction | The improvement in which a University employee feels self motivated, content and satisfied with his/her job. This is linked to job stability, career growth and a comfortable work life balance.
Increase in student satisfaction | The improvement in satisfaction usually resulting from a students educational experience, services and faculties.
Increased efficiency | The ability to accomplish the same thing with a reduction in the amount of time and effort required.
Increased productivity | The ability to do more with the same amount of time and effort.
Positive impact on reputation and / or brand awareness | An increase in how recognisable or memorable the University is to it’s target audience and how positively it is perceived.

## Slide 22
Financial Benefit Examples | Key tools for measurement / analysis | Suggested Measurement
Staff capacity savings | Process timing sheet | Processing time post-improvement compared to baseline processing time (% reduction) Time saved (hours) Cost saved (£)
Office space saved | Estates / Financial reports or charges | Space saved (m3) Cost charged for space (£)
Reduced costs / expenditure | Budget / Accounts reports Financial reports | Baseline inventory costs compared to inventory costs post-improvement (£ or % reduction) Baseline temporary staff expenditure
Increased Revenue to the Institution | Financial Statements Budget Reports | Total revenue for most recent financial year compared to total revenue at end of last financial year (£ or %)
Reduced Printing Costs | Manual Data Template Budgets/Accounts Reports | Number of pages saved Baseline Inventory costs compared to inventory costs post-improvement (£ or % reduction) Baseline shredding/removal/storage costs compared to costs post-improvement (£ or % reduction)
Appendix C2 – Example benefits and measures

## Slide 23
Non-financial Benefit Examples | Key tools for measurement / analysis | Suggested Measurement
Increased Quality | Visual Management Performance Measures Process Timing Sheets Lead Timing Sheets Pareto Charts | Baseline number of process steps complete and accurate compared to number post-improvement (% increase) Baseline number of errors received compared to number post-improvement (% reduction)
Removal of bottleneck | Visual Management Performance Measures Process Timing Sheets Lead Timing Sheets Pareto Charts Value Stream Map | Baseline number of process steps in bottleneck compared to number post-improvement (% reduction) Baseline staff expenditure for temporary staff to deal with bottleneck compared to expenditure post-improvement (£)
Reduced/Removed Backlog | Visual Management Performance Measures Process Timing Sheets Lead Timing Sheets Pareto Charts Value Stream Map | Baseline number of process steps in backlog compared to number post-improvement (% reduction) Baseline staff expenditure for temporary staff to deal with backlogs compared to expenditure post-improvement (£)
Appendix C2 – Example benefits and measures

## Slide 24
Non-financial Benefit Examples | Key tools for measurement / analysis | Suggested Measurement
Reduction in waste/rework/ errors | • Visual Management • Performance Measures • Process Timing Sheets • Lead Timing Sheets • Pareto Charts | Baseline number of errors received compared to number post-improvement (% reduction) Baseline number of process steps complete and accurate compared to number post-improvement (% increase)
Increased Conversion Rate | Survey/Voice of the Customer Complaints | Establish baseline satisfaction levels with existing service; repeat Voice of the Customer after implementing improved way of working and compare results (% reduction) Baseline number of complaints received compared to number of complaints post-improvement (% reduction)
Improved Health & Safety Levels Improved compliance with external bodies | Audit Reports Health and Safety Reporting | Comparison of baseline audit results with audits postimprovements Number of Health and Safety incidents (% reduction compared to baseline number) Elapsed time since last incident
Reduced Emails | System Reports Manual Data Capturing | Baseline number of emails sent/received compared to number of emails post-improvement (% reduction)
Appendix C2 – Example benefits and measures

## Slide 25
Non-financial Benefit Examples | Key tools for measurement / analysis | Suggested Measurement
Reduced Telephone calls | System Reports Manual Data Capturing | Baseline number of calls received compared to number of calls post-improvement (% reduction
Improved Communications | Survey Manual Data Capturing System Reports (Email or Telephone) | Establish baseline satisfaction levels with existing communication approach; repeat survey after implementing improved way of working and compare results Baseline number of communications sent compared to number of communications post-improvement (% reduction)
Impact on environment/ society | Research Findings/Results Survey | Establish baseline satisfaction levels of indirect stakeholders who may be affected by the improvement; repeat survey after implementing improved way of working and compare results
Greater Productivity | Financial reports System Reports Manual Data Capture Benchmarking Sector reports KPIs/Performance Reports | Total staff hours available compared to total hours of work to be completed (%) Baseline quantity of work completed per year/hour compared to quantity of work completed per year/hour postimprovement (%) Staff costs as percentage of Institutional income (%)
Overall length of end to end process | System Reports Lead Timing Sheet Value Stream Map | Improved Lead Time (%) No of steps in the process (%)
Appendix C2 – Example benefits and measures

## Slide 26
Non-financial Benefit Examples | Key tools for measurement / analysis | Suggested Measurement
Upskilling of staff | Training/Workshop Reporting Survey | Number of staff engaged with project/workshops Delivery of training and development events Transfer of knowledge and skills to staff
Improved morale of team | Survey Human Resources Data (anonymous) | Establish baseline morale levels with existing process; repeat survey after implementing improved way of working and compare results Baseline annual sickness absence compared to absence post-improvement (% reduction)
Increased awareness of BPI | Training/Workshop Reporting | Staff who have engaged with project (%
Appendix C2 – Example benefits and measures

## Slide 27
Appendix D – Example of a Benefits Map
Benefits Mapping is a technique for identifying the benefits of a scheme, establishing how they link to project activities and demonstrating how they contribute to achieving strategic goals and objectives. Below is an example benefit map.
Benefit Mapping encourages a rigorous analysis of the relationships between project activities, the intended Benefits, Goals and Vision
Strategic Goal
How does the project link to the 5 year plan.
We will support the 5 year plan in these areas
Benefit / Disbenefit
The measurable improvement from the business change
Through these measurable improvements
Business Change
How things are done differently when an organisation improves.
(Also known as an Outcome)
By delivering this
Which are the result of these changes
Deliverables
The goods or services produced as a result of a project
(Also known as an Output)
Objectives
What the project is planning to achieve, this should link to the scope of the project.
From this project scope
Our people, our values
85% of our people will say the University is a good place to work
Financial sustainability
We will be generating operating cash of 10% of revenue before strategic expenditure
Innovation
We will be recognised as Europe's most innovative university
Cost avoidance of £30m potential fines Dec 2022
Increased effectiveness of data collection processes and the ability to process additional returns by Dec 2022
Faster processing of information leading to more returns being submitted by Dec 2022
Increased operational team resilience and staff confidence scores by Dec 2022
Reduction in quality checks and improved data quality and core data by Dec 2022
Improved student analytics and more resilient core data by Dec 2022
Removal of duplication in the data collection process
Consistent 'Right first time' data entry
A consistent level of knowledge and expertise across the team
Mandatory compliance with national data requirements
Implementation of new IT system
New efficient ways of working that are consistent across the university
Accurate quality data
Deliver a compliant data solution in line with conditions of registration.
Design and develop tools to streamline how the University currently collects, stores and processes the student data.
Enhance existing data tools, interfaces and processes to improve data definition, quality and reporting.
Design, develop and implement processes to improve and maintain accurate quality data across the university all year round in order to deliver multiple in-year returns.

## Slide 28
<Insert Project name> Benefit Mapping Session
Give a high level explanation of what the overall objective of the project is.
Benefits Mapping
A exercise to link the expected benefits of the project to the business change, project deliverables and University objectives, in order to provie a benefits plan to monitor through pre-implementation and post-implementation
Appendix E – Template for Benefit Mapping Workshop

## Slide 29
Appendix E - Benefits Mapping Workshop: Objectives
Allow 2 hours for the workshop to allow sufficient discussion time, the workshop will help to;
Ensure strategic alignment from programme/project objectives, deliverables, business changes, benefits and strategic goals.
Provide a common understanding on the purpose of the programme/ project to all stakeholders
Provide clarity and purpose on the programme/project goals within the team and facilitates alignment
Engage stakeholders in a passionate and exciting way to create buy-in
Support a one-team mentality within the programme/project, with workstreams focusing on a common goal

## Slide 30
Appendix E - Benefits Mapping Workshop: Key points to clarify
Confirm the key deliverables from the project
  What are we changing + delivering?
  What would the outcomes be from this activity?
  What activity goes into this?
Outline why we are delivering these changes
  What are the benefits of these business changes?
  Are they worded correctly to be measurable?
  Are there any more to add?
Identify how we can measure and track these benefits to show our progress
  What method of measurement could we use?
  What measures do we have available to us?
  Who should be our benefit owners?

## Slide 31
Appendix E- Benefits Mapping Workshop: Sample Agenda
Time | Activity | Who
15 mins | Introductions and project background | PM / Sponsor
Allow 45 mins | Benefits identification - An exercise to provide a picture of the individual benefits that the project is expected to deliver. E.g time savings, efficiency savings etc. | PM & PMO / Benefit Analyst
Allow 45 mins | Benefits mapping - An exercise to confirm the deliverables and business changes that will be required to deliver the expected benefits, the measures that will evidence this and how they map to the university objectives | PM & PMO / Benefit Analyst
15 mins | Close and next steps | PM / Sponsor